## 中文
If you have difficulty in reading Chinese, you can refer to the English Annotations on the next sheet.
任务名称 | 起始时间 | 完成时间 | 人员安排 | 备注
1.0预研和准备
研发总体计划
研发框架搭建. |  |  |  | 已提供
初始化开发和测试环境. |  |  |  | tomcat 8, redis 3.28, rabbitmq 3.6.12 ,elastic search | 12号前提供帐号
消息队列搭建和接口基础类预研 |  |  |  | 已搭好
调度策略算法预研 |  |  |  | 见《01-总体设计说明书开发版.pdf》
国际化功能预研 |  |  |  | 前端包提供了一些，后端要自己考虑实现
需求研究 |  |  |  | 需求文档已发
总体设计 |  |  |  | 已完成
参数配置功能研发 |  | 10月31号 |  | 需要做
查询功能研发 |  | 10月31号 |  | 需要做
命令转发功能研发 |  | 10月31号 |  | 需要做
节点异常处理 |  | 10月31号 |  | 需要做
网络异常处理 |  | 10月31号 |  | 需要做
与其他模块接口研发 |  | 10月31号 |  | 需要做
文件上传、图像存储研发 |  | 10月31号 |  | 需要做
打印、导入、导出功能研发 |  | 10月31号 |  | 需要做
统计报表功能研发 |  | 10月31号 |  | 需要做
调度任务管理功能研发 |  | 10月31号 |  | 需要做
安全防护功能研发 |  | 10月31号 |  | 需要做
zabbix搭建和基本功能处理 |  | 10月31号 |  | 需要做
1.1文档 |  | 10月31号
1.1.1 UI设计 |  | 10月18号 |  | 先做首页、UI主要是先画一部分，威视定UI设计风格
1.1.2需求规格说明书 |  | 10月18号 |  | 10月11日先做权限管理、设备管理，18日前全部做完
1.1.3页面原型 |  | 10月18号 |  | 10月11日先做权限管理、设备管理，18日前全部做完
1.1.4测试用例 |  | 11月10号 | 测试用例.xlsx | 开发人员自己写
1.2 功能需求 |  | 11月10号 |  | 放在后面做
1.2.1 功能需求 |  | 11月10号
1.2.3 后台服务 |  | 11月10号
1.2.3.1 后台服务 |  | 11月10号
1.2.3.2 图像存储 |  | 11月10号
1.2.3.3 多对多，智能分发 |  | 11月10号
1.2.3.4 存储空间监控 |  | 11月10号
1.2.3.5 定时任务 |  | 11月10号
1.2.3.6 设备控制命令转发 |  | 11月10号
1.2.5 集中管理 |  | 10月31号 |  | 黄色背景，建议在10月31日前完成；其他的11月10日前完成
1.2.5.1 集中管理 |  | 10月31号
1.2.5.2 图像管理 |  | 10月31号
1.2.5.2.1 图像管理 |  | 10月31号
1.2.5.2.2 删除图像 |  | 10月31号
1.2.5.2.3 图像处理 |  | 10月31号
1.2.5.2.4 图像标签管理 |  | 10月31号
1.2.5.2.5 检索图像 |  | 10月31号
1.2.5.2.6 预览图像 |  | 10月31号
1.2.5.2.7 导出图像 |  | 10月31号
1.2.5.2.8 打印图像 |  | 10月31号
1.2.5.3 数据统计 |  | 11月10号 |  | 放在后面
1.2.5.3.1 数据统计 |  | 11月10号
1.2.5.3.2 判图员审图统计 |  | 11月10号
1.2.5.3.3 图像统计 |  | 11月10号
1.2.5.3.4 手检员工作统计 |  | 11月10号
1.2.5.3.5 打印统计报表 |  | 11月10号
1.2.5.3.6 报警物品统计 |  | 11月10号
1.2.5.3.7 报警部位统计 |  | 11月10号
1.2.5.3.8 登录时长统计 |  | 11月10号
1.2.5.3.9 统计报表导出到Excel |  | 11月10号
1.2.5.3.10 设备工作统计 |  | 11月10号
1.2.5.4 日志管理 |  | 11月10号 |  | 放在后面
1.2.5.4.1 日志管理 |  | 11月10号
1.2.5.4.2 查询用户登录日志 |  | 11月10号
1.2.5.4.3 查询设备开机日志 |  | 11月10号
1.2.5.4.4 查询设备运行日志 |  | 11月10号
1.2.5.4.5 查询系统日志 |  | 11月10号
1.2.5.4.6 查询操作日志 |  | 11月10号
1.2.5.4.7 导出日志 |  | 11月10号
1.2.5.4.8 打印日志 |  | 11月10号
1.2.5.5 设备管理 |  | 10月31号
1.2.5.5.1 设备管理 |  | 10月31号
1.2.5.5.2 设备组管理 |  | 10月31号
1.2.5.5.2.1 设备组管理 |  | 10月31号
1.2.5.5.2.2 删除设备组 |  | 10月31号
1.2.5.5.2.3 添加设备组 |  | 10月31号
1.2.5.5.2.4 重命名设备组 |  | 10月31号
1.2.5.5.3 集中参数配置 |  | 10月31号
1.2.5.5.3.1 集中参数配置 |  | 10月31号
1.2.5.5.3.2 后台服务 |  | 10月31号
1.2.5.5.3.2.1 后台服务 |  | 10月31号
1.2.5.5.3.2.2 图像存储方式配置 |  | 10月31号
1.2.5.5.3.2.3 存储空间阈值 |  | 10月31号
1.2.5.5.3.2.4 调度策略配置 |  | 10月31号
1.2.5.5.3.2.5 跳过黑名单图检任务 |  | 10月31号
1.2.5.5.3.3 审图端 |  | 10月31号
1.2.5.5.3.3.1 审图端 |  | 10月31号
1.2.5.5.3.3.2 单幅图审图时间 |  | 10月31号
1.2.5.5.3.3.3 累计工作时长提醒阈值 |  | 10月31号
1.2.5.5.3.4 手检站 |  | 10月31号
1.2.5.5.3.4.1 手检站 |  | 10月31号
1.2.5.5.3.4.2 累计工作时长提醒阈值 |  | 10月31号
1.2.5.5.3.5 设备端 |  | 10月31号
1.2.5.5.3.5.1 设备端 |  | 10月31号
1.2.5.5.3.5.2 工作模式 |  | 10月31号
1.2.5.5.3.5.3 提示声音开关 |  | 10月31号
1.2.5.5.3.5.4 数据保存 |  | 10月31号
1.2.5.5.3.5.5 本机手检 |  | 10月31号
1.2.5.5.3.5.6 模糊处理 |  | 10月31号
1.2.5.5.3.5.7 流量参数设置 |  | 10月31号
1.2.5.5.3.5.8 罩板校正时间 |  | 10月31号
1.2.5.5.3.5.9 自动识别配置 |  | 10月31号
1.2.5.5.3.5.10 设备端待机时间 |  | 10月31号
1.2.5.5.4 毫米波设备管理 |  | 10月31号
1.2.5.5.5 添加毫米波设备 |  | 10月31号
1.2.5.5.6 编辑毫米波设备 |  | 10月31号
1.2.5.5.7 删除毫米波设备 |  | 10月31号
1.2.5.5.8 审图客户端管理 |  | 10月31号
1.2.5.5.9 添加审图客户端 |  | 10月31号
1.2.5.5.10 编辑审图客户端 |  | 10月31号
1.2.5.5.11 删除审图客户端 |  | 10月31号
1.2.5.5.12 移动查验端管理 |  | 10月31号
1.2.5.5.13 添加移动查验端 |  | 10月31号
1.2.5.5.14 编辑移动查验端 |  | 10月31号
1.2.5.5.15 删除移动查验端 |  | 10月31号
1.2.5.5.16 集中监控 |  | 10月31号
1.2.5.5.17 卡片式显示所有毫米波设备 |  | 10月31号
1.2.5.5.18 卡片式显示所有审图客户端 |  | 10月31号
1.2.5.5.19 卡片式显示所有移动查验端 |  | 10月31号
1.2.5.5.20 设备模板 |  | 10月31号
1.2.5.5.21 设备档案 |  | 10月31号
1.2.5.5.22 设备列表 |  | 10月31号
1.2.5.6 黑名单管理 |  | 10月31号
1.2.5.6.1 黑名单管理 |  | 10月31号
1.2.5.6.2 查询黑名单人员 |  | 10月31号
1.2.5.6.3 添加黑名单人员 |  | 10月31号
1.2.5.6.4 编辑黑名单人员 |  | 10月31号
1.2.5.7 用户管理 |  | 10月31号
1.2.5.7.1 用户管理 |  | 10月31号
1.2.5.7.2 到出用户到Excel |  | 10月31号
1.2.5.7.3 打印用户 |  | 10月31号
1.2.5.7.4 用户快速定位 |  | 10月31号
1.2.5.7.5 用户组管理 |  | 10月31号
1.2.5.7.6 角色权限管理 |  | 10月31号
1.2.5.7.7 角色管理 |  | 10月31号
1.2.5.7.8 帐号管理 |  | 10月31号
1.2.5.8 维保管理 |  | 10月31号
1.2.5.8.1 维保管理 |  | 10月31号
1.2.5.8.2 维保项目管理 |  | 10月31号
1.2.5.8.3 登记维保记录 |  | 10月31号
1.2.5.8.4 审核维保记录 |  | 10月31号
1.2.5.8.5 查询维保记录 |  | 10月31号
1.2.5.8.6 打印维保记录 |  | 10月31号
1.2.5.9 业务管理 |  | 10月31号
1.2.5.9.1 业务管理 |  | 10月31号
1.2.5.9.2 查验任务状态监控 |  | 10月31号
1.2.5.10 知识库管理 |  | 11月10号 |  | 放在后面
1.2.5.10.1 知识库管理 |  | 11月10号
1.2.5.10.2 删除知识库案例 |  | 11月10号
1.2.5.10.3 检索知识库案例 |  | 11月10号
1.2.5.10.4 添加知识库案例 |  | 11月10号
1.3 非功能需求 |  | 11月10号
1.3.1 非功能需求 |  | 11月10号
1.3.2 安全性 |  | 11月10号
1.3.2.1 安全性 |  | 11月10号
1.3.2.2 REQ905-注册的设备方可联入系统 |  | 11月10号
1.3.2.3 REQ901-所有信息加密存储 |  | 11月10号
1.3.2.4 REQ902-数据/消息加密传输 |  | 11月10号
1.3.2.5 REQ903-授权的用户方可操作系统 |  | 11月10号
1.3.2.6 REQ904-核心服务/数据多机热备 |  | 11月10号
其他安全性设计 |  | 11月10号
1.3.3 容错性 |  | 11月10号
1.3.3.1 容错性 |  | 11月10号
1.3.3.2 网络异常 |  | 11月10号
1.3.3.3 节点异常 |  | 11月10号
1.3.4 性能 |  | 11月10号
1.3.4.1 性能 |  | 11月10号
1.3.4.2 REQ921-常用操作无明显延迟感 |  | 11月10号
1.3.4.3 REQ922-集中审图允许接入毫米波设备要大于等于200台 |  | 11月10号
1.3.4.4 REQ923-扫描完成调度加传输时间小于等于1秒 |  | 11月10号
1.3.4.5 REQ924-高稳定性 |  | 11月10号
1.3.5 扩展性 |  | 11月10号
1.3.5.1 扩展性 |  | 11月10号
1.3.5.2 REQ941-接口化设计 |  | 11月10号
1.3.5.3 REQ942-插件化设计 |  | 11月10号
1.3.5.4 REQ943-模块化设计 |  | 11月10号
1.3.5.5 REQ944-RESTful |  | 11月10号
1.3.5.6 REQ945-支持离线工作模式 |  | 11月10号
1.3.5.7 REQ946-工作模式灵活部署 |  | 11月10号
1.3.5.8 REQ947-设备节点灵活部署 |  | 11月10号
1.3.5.9 REQ948-支持第三方系统集成 |  | 11月10号
1.3.5.10 REQ949-支持多种分辨率 |  | 11月10号
浏览器适配 |  | 11月10号
其他开发任务 |  | 11月10号
1.4 测试 |  | 11月10号
1.4.1 安全测试 |  | 11月10号
1.4.2 性能测试 |  | 11月10号
1.4.3 功能测试 |  | 11月10号
1.5 联调 |  | 11月10号
1.6 部署和验收 |  | 11月10号
1.7 编写文档 |  | 11月10号
5)子模块概要设计说明书 |  | 11月10号
6)UI设计效果 |  | 11月10号
7)子模块测试用例说明书 |  | 11月10号
8)子模块详细设计说明书(可选) |  | 11月10号
9)代码 |  | 11月10号
10)系统测试报告 |  | 11月10号
11)安装手册 |  | 11月10号
12)操作手册 |  | 11月10号
1.5 功能联调测试 | 11月11号 | 12月20号

## English
Task name | Starting time | Completion time | Resource arrangement | note
1.0Pre-research and preparation
developing plan
framework
Initialize the development and test environment.
Pre-research on Message Queue Building and Interface Foundation Class
Pre-research on Scheduling Strategy Algorithms
Pre-research on Internationalization Function
requiement study
overall design
Research and Development of Parameter Configuration Function
Research and Development of Query Function
Research and Development of Command Forwarding Function
Node exception handling
Network exception handling
Research and development of interface with other modules
Research and Development of File Upload and Image Storage
Research and Development of Printing, Importing and Exporting Functions
Research and Development of Statistical Report Function
Research and Development of Scheduling Task Management Function
Research and Development of Safety Protection Function
Zabbix Construction and Basic Function Processing
1.1 UI design
1.2 Functional Requirements
1.2.1 Functional Requirements
1.2.3 Backstage Service
1.2.3.1 Backstage Service
1.2.3.2 Image Storage
1.2.3.3 Multi-to-Many, Intelligent Distribution
1.2.3.4 Storage Space Monitoring
1.2.3.5 Timing Tasks
1.2.3.6 Device Control Command Forwarding
1.2.5 Centralized Management
1.2.5.1 Centralized Management
1.2.5.2 Image Management
1.2.5.2.1 Image Management
1.2.5.2.2 Delete Image
1.2.5.2.3 Image Processing
1.2.5.2.4 Image Label Management
1.2.5.2.5 Retrieval Image
1.2.5.2.6 Preview image
1.2.5.2.7 Export Image
1.2.5.2.8 Printed Image
1.2.5.3 Data Statistics
1.2.5.3.1 Data Statistics
1.2.5.3.2 Map Checking Statistics of Judgers
1.2.5.3.3 Image Statistics
1.2.5.3.4 Hand Checker Work Statistics
1.2.5.3.5 Print statistical reports
1.2.5.3.6 Statistics of alarm items
1.2.5.3.7 alarm location statistics
1.2.5.3.8 Logon Length Statistics
1.2.5.3.9 Statistical Report Exported to Excel
1.2.5.3.10 Equipment Work Statistics
1.2.5.4 Log Management
1.2.5.4.1 Log Management
1.2.5.4.2 Query User Log
1.2.5.4.3 Query Device Boot Log
1.2.5.4.4 Query Equipment Operation Log
1.2.5.4.5 Query System Log
1.2.5.4.6 Query Operational Log
1.2.5.4.7 Export Log
1.2.5.4.8 Printed Log
1.2.5.5 Equipment Management
1.2.5.5.1 Equipment Management
1.2.5.5.2 Equipment Group Management
1.2.5.5.2.1 Equipment Group Management
1.2.5.5.2.2 Delete Device Group
1.2.5.5.2.3 Add Device Group
1.2.5.5.2.4 Rename Device Group
1.2.5.5.3 lumped parameter configuration
1.2.5.5.3.1 lumped parameter configuration
1.2.5.5.3.2 Backstage Service
1.2.5.5.3.2.1 Backstage Service
1.2.5.5.3.2.2 Image storage configuration
1.2.5.5.3.2.3 Storage Space Threshold
1.2.5.5.3.2.4 Scheduling Policy Configuration
1.2.5.5.3.2.5 Skip Blacklist Mapping Task
1.2.5.5.3.3 Examination End
1.2.5.5.3.3.1 Examination End
1.2.5.5.3.3.2 Map Examination Time for Single Map
1.2.5.5.3.3.3 Cumulative Working Time Reminder Threshold
1.2.5.5.3.4 Hand-check Station
1.2.5.5.3.4.1 Hand Check Station
1.2.5.5.3.4.2 Cumulative Work Time Reminder Threshold
1.2.5.5.3.5 device end
1.2.5.5.3.5.1 Equipment End
1.2.5.5.3.5.2 working mode
1.2.5.5.3.5.3 prompt sound switch
1.2.5.5.3.5.4 Data Preservation
1.2.5.5.3.5.5 Hand-check of this machine
1.2.5.5.3.5.6 Fuzzy Processing
1.2.5.5.3.5.7 Flow Parameter Settings
1.2.5.5.3.5.8 Shield Correction Time
1.2.5.5.3.5.9 Automatic Identification Configuration
1.2.5.5.3.5.10 equipment standby time
1.2.5.5.4 mm-wave equipment management
1.2.5.5.5 Adding Millimeter Wave Equipment
1.2.5.5.6 Editing Millimeter Wave Equipment
1.2.5.5.7 Delete Millimeter Wave Devices
1.2.5.5.8 Mapping Client Management
1.2.5.5.9 Add Mapping Client
1.2.5.5.10 Editing and Mapping Client
1.2.5.5.11 Delete Mapping Client
1.2.5.5.12 Mobile Checker Management
1.2.5.5.13 Add mobile checker
1.2.5.5.14 Editor Mobile Checker
1.2.5.5.15 Delete mobile checker
1.2.5.5.16 Centralized Monitoring
1.2.5.5.17 Card Display All Millimeter Wave Equipment
1.2.5.5.18 Card Display All Examination Clients
1.2.5.5.19 card display for all mobile checkers
1.2.5.6 Blacklist Management
1.2.5.6.1 Blacklist Management
1.2.5.6.2 Query Blacklist Personnel
1.2.5.6.3 Adding Blacklist Personnel
1.2.5.6.4 Blacklist Editors
1.2.5.7 User Management
1.2.5.7.1 User Management
1.2.5.7.2 to Outgoing User to Excel
1.2.5.7.3 Print User
1.2.5.7.4 User Rapid Location
1.2.5.7.5 User Group Management
1.2.5.7.6 Role Privilege Management
1.2.5.7.7 Role Management
1.2.5.7.8 Account Management
1.2.5.8 Maintenance Management
1.2.5.8.1 Maintenance Management
1.2.5.8.2 Maintenance Project Management
1.2.5.8.3 Registration and Maintenance Records
1.2.5.8.4 Audit and Maintenance Records
1.2.5.8.5 Query Maintenance Records
1.2.5.8.6 Print Maintenance Records
1.2.5.9 Business Management
1.2.5.9.1 Business Management
1.2.5.9.2 Check Task Status Monitoring
1.2.5.10 Knowledge Base Management
1.2.5.10.1 Knowledge Base Management
1.2.5.10.2 Deletion of Knowledge Base Cases
1.2.5.10.3 Retrieval Knowledge Base Cases
1.2.5.10.4 Adding Knowledge Base Cases
1.3 Non-functional Requirements
1.3.1 Non-functional Requirements
1.3.2 Security
1.3.2.1 Security
1.3.2.2 REQ905 - Registered equipment can be connected to the system
1.3.2.3 REQ901 - Encrypted storage of all information
1.3.2.4 REQ902-Data/Message Encrypted Transport
1.3.2.5 REQ903- authorized user can operate system
1.3.2.6 REQ904 - Core Services/Data Multi-machine Hot Standby
Other security design
1.3.3 fault tolerance
1.3.3.1 Fault Tolerance
1.3.3.2 Network Abnormality
1.3.3.3 node exception
1.3.4 Performance
1.3.4.1 Performance
1.3.4.2 REQ921 - No significant sense of delay in common operations
1.3.4.3 REQ922 - Centralized Mapping allows access to more than 200 millimeter wave devices
1.3.4.4 REQ923 - Scan completion scheduling plus transmission time less than or equal to 1 second
1.3.4.5 REQ924 - High stability
1.3.5 Extension
1.3.5.1 Extension
1.3.5.2 REQ941-Interface Design
1.3.5.3 REQ942-Plug-in Design
1.3.5.4 REQ943-Modular Design
1.3.5.5 REQ944-RESTful
1.3.5.6 REQ945 - Support offline working mode
1.3.5.7 REQ946 - Flexible deployment of working mode
1.3.5.8 REQ947 - Flexible deployment of device nodes
1.3.5.9 REQ948 - Support for third-party system integration
1.3.5.10 REQ949 - Supports multiple resolutions
Browser adaptation
Other tasks
1.4 test
1.4.1 Security Test
1.4.2 Performance Test
1.4.3 Functional Test
1.5 tune ups
1.6 Deployment and Acceptance
1.7 Documentation
5) Summary of Submodule Design
6) UI design effect
7) Submodule test case specification
8) Detailed design instructions for sub-modules (optional)
9) code
10) System Test Report
11) Installation Manual
12) Manual

## 일정
任务名称 | 完成时间 | 备注
1.0预研和准备
研发总体计划
研发框架搭建. |  | 已提供
初始化开发和测试环境. |  | tomcat 8, redis 3.28, rabbitmq 3.6.12 ,elastic search | 12号前提供帐号
消息队列搭建和接口基础类预研 |  | 已搭好
调度策略算法预研 |  | 见《01-总体设计说明书开发版.pdf》
国际化功能预研 |  | 前端包提供了一些，后端要自己考虑实现
需求研究 |  | 需求文档已发
总体设计 |  | 已完成
参数配置功能研发 | 10月31号 | 需要做
查询功能研发 | 10月31号 | 需要做
命令转发功能研发 | 10月31号 | 需要做
节点异常处理 | 10月31号 | 需要做
网络异常处理 | 10月31号 | 需要做
与其他模块接口研发 | 10月31号 | 需要做
文件上传、图像存储研发 | 10月31号 | 需要做
打印、导入、导出功能研发 | 10月31号 | 需要做
统计报表功能研发 | 10月31号 | 需要做
调度任务管理功能研发 | 10月31号 | 需要做
安全防护功能研发 | 10月31号 | 需要做
zabbix搭建和基本功能处理 | 10月31号 | 需要做
1.1文档 | 10月31号
1.1.1 UI设计 | 10月18号 | 先做首页、UI主要是先画一部分，威视定UI设计风格
1.1.2需求规格说明书 | 10月18号 | 10月11日先做权限管理、设备管理，18日前全部做完
1.1.3页面原型 | 10月18号 | 10月11日先做权限管理、设备管理，18日前全部做完
1.1.4测试用例 | 11月10号 | 开发人员自己写, 测试用例.xlsx
1.2 功能需求 | 11月10号 | 放在后面做
1.2.1 功能需求 | 11月10号
1.2.3 后台服务 | 11月10号
1.2.3.1 后台服务 | 11月10号
1.2.3.2 图像存储 | 11月10号
1.2.3.3 多对多，智能分发 | 11月10号
1.2.3.4 存储空间监控 | 11月10号
1.2.3.5 定时任务 | 11月10号
1.2.3.6 设备控制命令转发 | 11月10号
1.2.5 集中管理 | 10月31号 | 黄色背景，建议在10月31日前完成；其他的11月10日前完成
1.2.5.1 集中管理 | 10月31号
1.2.5.2 图像管理 | 10月31号
1.2.5.2.1 图像管理 | 10月31号
1.2.5.2.2 删除图像 | 10月31号
1.2.5.2.3 图像处理 | 10月31号
1.2.5.2.4 图像标签管理 | 10月31号
1.2.5.2.5 检索图像 | 10月31号
1.2.5.2.6 预览图像 | 10月31号
1.2.5.2.7 导出图像 | 10月31号
1.2.5.2.8 打印图像 | 10月31号
1.2.5.3 数据统计 | 11月10号 | 放在后面
1.2.5.3.1 数据统计 | 11月10号
1.2.5.3.2 判图员审图统计 | 11月10号
1.2.5.3.3 图像统计 | 11月10号
1.2.5.3.4 手检员工作统计 | 11月10号
1.2.5.3.5 打印统计报表 | 11月10号
1.2.5.3.6 报警物品统计 | 11月10号
1.2.5.3.7 报警部位统计 | 11月10号
1.2.5.3.8 登录时长统计 | 11月10号
1.2.5.3.9 统计报表导出到Excel | 11月10号
1.2.5.3.10 设备工作统计 | 11月10号
1.2.5.4 日志管理 | 11月10号 | 放在后面
1.2.5.4.1 日志管理 | 11月10号
1.2.5.4.2 查询用户登录日志 | 11月10号
1.2.5.4.3 查询设备开机日志 | 11月10号
1.2.5.4.4 查询设备运行日志 | 11月10号
1.2.5.4.5 查询系统日志 | 11月10号
1.2.5.4.6 查询操作日志 | 11月10号
1.2.5.4.7 导出日志 | 11月10号
1.2.5.4.8 打印日志 | 11月10号
1.2.5.5 设备管理 | 10月31号
1.2.5.5.1 设备管理 | 10月31号
1.2.5.5.2 设备组管理 | 10月31号
1.2.5.5.2.1 设备组管理 | 10月31号
1.2.5.5.2.2 删除设备组 | 10月31号
1.2.5.5.2.3 添加设备组 | 10月31号
1.2.5.5.2.4 重命名设备组 | 10月31号
1.2.5.5.3 集中参数配置 | 10月31号
1.2.5.5.3.1 集中参数配置 | 10月31号
1.2.5.5.3.2 后台服务 | 10月31号
1.2.5.5.3.2.1 后台服务 | 10月31号
1.2.5.5.3.2.2 图像存储方式配置 | 10月31号
1.2.5.5.3.2.3 存储空间阈值 | 10月31号
1.2.5.5.3.2.4 调度策略配置 | 10月31号
1.2.5.5.3.2.5 跳过黑名单图检任务 | 10月31号
1.2.5.5.3.3 审图端 | 10月31号
1.2.5.5.3.3.1 审图端 | 10月31号
1.2.5.5.3.3.2 单幅图审图时间 | 10月31号
1.2.5.5.3.3.3 累计工作时长提醒阈值 | 10月31号
1.2.5.5.3.4 手检站 | 10月31号
1.2.5.5.3.4.1 手检站 | 10月31号
1.2.5.5.3.4.2 累计工作时长提醒阈值 | 10月31号
1.2.5.5.3.5 设备端 | 10月31号
1.2.5.5.3.5.1 设备端 | 10月31号
1.2.5.5.3.5.2 工作模式 | 10月31号
1.2.5.5.3.5.3 提示声音开关 | 10月31号
1.2.5.5.3.5.4 数据保存 | 10月31号
1.2.5.5.3.5.5 本机手检 | 10月31号
1.2.5.5.3.5.6 模糊处理 | 10月31号
1.2.5.5.3.5.7 流量参数设置 | 10月31号
1.2.5.5.3.5.8 罩板校正时间 | 10月31号
1.2.5.5.3.5.9 自动识别配置 | 10月31号
1.2.5.5.3.5.10 设备端待机时间 | 10月31号
1.2.5.5.4 毫米波设备管理 | 10月31号
1.2.5.5.5 添加毫米波设备 | 10月31号
1.2.5.5.6 编辑毫米波设备 | 10月31号
1.2.5.5.7 删除毫米波设备 | 10月31号
1.2.5.5.8 审图客户端管理 | 10月31号
1.2.5.5.9 添加审图客户端 | 10月31号
1.2.5.5.10 编辑审图客户端 | 10月31号
1.2.5.5.11 删除审图客户端 | 10月31号
1.2.5.5.12 移动查验端管理 | 10月31号
1.2.5.5.13 添加移动查验端 | 10月31号
1.2.5.5.14 编辑移动查验端 | 10月31号
1.2.5.5.15 删除移动查验端 | 10月31号
1.2.5.5.16 集中监控 | 10月31号
1.2.5.5.17 卡片式显示所有毫米波设备 | 10月31号
1.2.5.5.18 卡片式显示所有审图客户端 | 10月31号
1.2.5.5.19 卡片式显示所有移动查验端 | 10月31号
1.2.5.5.20 设备模板 | 10月31号
1.2.5.5.21 设备档案 | 10月31号
1.2.5.5.22 设备列表 | 10月31号
1.2.5.6 黑名单管理 | 10月31号
1.2.5.6.1 黑名单管理 | 10月31号
1.2.5.6.2 查询黑名单人员 | 10月31号
1.2.5.6.3 添加黑名单人员 | 10月31号
1.2.5.6.4 编辑黑名单人员 | 10月31号
1.2.5.7 用户管理 | 10月31号
1.2.5.7.1 用户管理 | 10月31号
1.2.5.7.2 到出用户到Excel | 10月31号
1.2.5.7.3 打印用户 | 10月31号
1.2.5.7.4 用户快速定位 | 10月31号
1.2.5.7.5 用户组管理 | 10月31号
1.2.5.7.6 角色权限管理 | 10月31号
1.2.5.7.7 角色管理 | 10月31号
1.2.5.7.8 帐号管理 | 10月31号
1.2.5.8 维保管理 | 10月31号
1.2.5.8.1 维保管理 | 10月31号
1.2.5.8.2 维保项目管理 | 10月31号
1.2.5.8.3 登记维保记录 | 10月31号
1.2.5.8.4 审核维保记录 | 10月31号
1.2.5.8.5 查询维保记录 | 10月31号
1.2.5.8.6 打印维保记录 | 10月31号
1.2.5.9 业务管理 | 10月31号
1.2.5.9.1 业务管理 | 10月31号
1.2.5.9.2 查验任务状态监控 | 10月31号
1.2.5.10 知识库管理 | 11月10号 | 放在后面
1.2.5.10.1 知识库管理 | 11月10号
1.2.5.10.2 删除知识库案例 | 11月10号
1.2.5.10.3 检索知识库案例 | 11月10号
1.2.5.10.4 添加知识库案例 | 11月10号
1.3 非功能需求 | 11月10号
1.3.1 非功能需求 | 11月10号
1.3.2 安全性 | 11月10号
1.3.2.1 安全性 | 11月10号
1.3.2.2 REQ905-注册的设备方可联入系统 | 11月10号
1.3.2.3 REQ901-所有信息加密存储 | 11月10号
1.3.2.4 REQ902-数据/消息加密传输 | 11月10号
1.3.2.5 REQ903-授权的用户方可操作系统 | 11月10号
1.3.2.6 REQ904-核心服务/数据多机热备 | 11月10号
其他安全性设计 | 11月10号
1.3.3 容错性 | 11月10号
1.3.3.1 容错性 | 11月10号
1.3.3.2 网络异常 | 11月10号
1.3.3.3 节点异常 | 11月10号
1.3.4 性能 | 11月10号
1.3.4.1 性能 | 11月10号
1.3.4.2 REQ921-常用操作无明显延迟感 | 11月10号
1.3.4.3 REQ922-集中审图允许接入毫米波设备要大于等于200台 | 11月10号
1.3.4.4 REQ923-扫描完成调度加传输时间小于等于1秒 | 11月10号
1.3.4.5 REQ924-高稳定性 | 11月10号
1.3.5 扩展性 | 11月10号
1.3.5.1 扩展性 | 11月10号
1.3.5.2 REQ941-接口化设计 | 11月10号
1.3.5.3 REQ942-插件化设计 | 11月10号
1.3.5.4 REQ943-模块化设计 | 11月10号
1.3.5.5 REQ944-RESTful | 11月10号
1.3.5.6 REQ945-支持离线工作模式 | 11月10号
1.3.5.7 REQ946-工作模式灵活部署 | 11月10号
1.3.5.8 REQ947-设备节点灵活部署 | 11月10号
1.3.5.9 REQ948-支持第三方系统集成 | 11月10号
1.3.5.10 REQ949-支持多种分辨率 | 11月10号
浏览器适配 | 11月10号
其他开发任务 | 11月10号
1.4 测试 | 11月10号
1.4.1 安全测试 | 11月10号
1.4.2 性能测试 | 11月10号
1.4.3 功能测试 | 11月10号
1.5 联调 | 11月10号
1.6 部署和验收 | 11月10号
1.7 编写文档 | 11月10号
5)子模块概要设计说明书 | 11月10号
6)UI设计效果 | 11月10号
7)子模块测试用例说明书 | 11月10号
8)子模块详细设计说明书(可选) | 11月10号
9)代码 | 11月10号
10)系统测试报告 | 11月10号
11)安装手册 | 11月10号
12)操作手册 | 11月10号
1.5 功能联调测试 | 12月20号