## 中文
If you have difficulty in reading Chinese, you can refer to the English Annotations on the next sheet.
任务名称 | 起始时间 | 完成时间 | 人员安排 | 备注
1.0预研和准备
研发总体计划
研发框架搭建. |  |  | 开发框架.zip | 비밀보장할것,전후단요구
初始化开发和测试环境. |  |  | Server 설치(10.12일전 보장)
消息队列搭建和接口基础类预研 |  |  | 이미 준비함(보)
调度策略算法预研 |  |  | 01-总体设计说明书开发版.pdf | 알고리듬 참고할것
国际化功能预研 |  |  | 전후단 언어팩 설치문제
需求研究 |  |  | 毫米波集中查验需求模型929-New.pdf | 요구서 볼것
总体设计
参数配置功能研发 |  |  | 개발할것(설계시 나옴)
查询功能研发 |  |  | 개발할것
命令转发功能研发
节点异常处理
网络异常处理
与其他模块接口研发
文件上传、图像存储研发
打印、导入、导出功能研发
统计报表功能研发
调度任务管理功能研发
安全防护功能研发
zabbix搭建和基本功能处理
1.1 UI设计
1.2 功能需求
1.2.1 功能需求
1.2.3 后台服务
1.2.3.1 后台服务
1.2.3.2 图像存储
1.2.3.3 多对多，智能分发
1.2.3.4 存储空间监控
1.2.3.5 定时任务
1.2.3.6 设备控制命令转发
1.2.5 集中管理
1.2.5.1 集中管理
1.2.5.2 图像管理
1.2.5.2.1 图像管理
1.2.5.2.2 删除图像
1.2.5.2.3 图像处理
1.2.5.2.4 图像标签管理
1.2.5.2.5 检索图像
1.2.5.2.6 预览图像
1.2.5.2.7 导出图像
1.2.5.2.8 打印图像
1.2.5.3 数据统计
1.2.5.3.1 数据统计
1.2.5.3.2 判图员审图统计
1.2.5.3.3 图像统计
1.2.5.3.4 手检员工作统计
1.2.5.3.5 打印统计报表
1.2.5.3.6 报警物品统计
1.2.5.3.7 报警部位统计
1.2.5.3.8 登录时长统计
1.2.5.3.9 统计报表导出到Excel
1.2.5.3.10 设备工作统计
1.2.5.4 日志管理
1.2.5.4.1 日志管理
1.2.5.4.2 查询用户登录日志
1.2.5.4.3 查询设备开机日志
1.2.5.4.4 查询设备运行日志
1.2.5.4.5 查询系统日志
1.2.5.4.6 查询操作日志
1.2.5.4.7 导出日志
1.2.5.4.8 打印日志
1.2.5.5 设备管理
1.2.5.5.1 设备管理
1.2.5.5.2 设备组管理
1.2.5.5.2.1 设备组管理
1.2.5.5.2.2 删除设备组
1.2.5.5.2.3 添加设备组
1.2.5.5.2.4 重命名设备组
1.2.5.5.3 集中参数配置
1.2.5.5.3.1 集中参数配置
1.2.5.5.3.2 后台服务
1.2.5.5.3.2.1 后台服务
1.2.5.5.3.2.2 图像存储方式配置
1.2.5.5.3.2.3 存储空间阈值
1.2.5.5.3.2.4 调度策略配置
1.2.5.5.3.2.5 跳过黑名单图检任务
1.2.5.5.3.3 审图端
1.2.5.5.3.3.1 审图端
1.2.5.5.3.3.2 单幅图审图时间
1.2.5.5.3.3.3 累计工作时长提醒阈值
1.2.5.5.3.4 手检站
1.2.5.5.3.4.1 手检站
1.2.5.5.3.4.2 累计工作时长提醒阈值
1.2.5.5.3.5 设备端
1.2.5.5.3.5.1 设备端
1.2.5.5.3.5.2 工作模式
1.2.5.5.3.5.3 提示声音开关
1.2.5.5.3.5.4 数据保存
1.2.5.5.3.5.5 本机手检
1.2.5.5.3.5.6 模糊处理
1.2.5.5.3.5.7 流量参数设置
1.2.5.5.3.5.8 罩板校正时间
1.2.5.5.3.5.9 自动识别配置
1.2.5.5.3.5.10 设备端待机时间
1.2.5.5.4 毫米波设备管理
1.2.5.5.5 添加毫米波设备
1.2.5.5.6 编辑毫米波设备
1.2.5.5.7 删除毫米波设备
1.2.5.5.8 审图客户端管理
1.2.5.5.9 添加审图客户端
1.2.5.5.10 编辑审图客户端
1.2.5.5.11 删除审图客户端
1.2.5.5.12 移动查验端管理
1.2.5.5.13 添加移动查验端
1.2.5.5.14 编辑移动查验端
1.2.5.5.15 删除移动查验端
1.2.5.5.16 集中监控
1.2.5.5.17 卡片式显示所有毫米波设备
1.2.5.5.18 卡片式显示所有审图客户端
1.2.5.5.19 卡片式显示所有移动查验端
1.2.5.6 黑名单管理
1.2.5.6.1 黑名单管理
1.2.5.6.2 查询黑名单人员
1.2.5.6.3 添加黑名单人员
1.2.5.6.4 编辑黑名单人员
1.2.5.7 用户管理
1.2.5.7.1 用户管理
1.2.5.7.2 到出用户到Excel
1.2.5.7.3 打印用户
1.2.5.7.4 用户快速定位
1.2.5.7.5 用户组管理
1.2.5.7.6 角色权限管理
1.2.5.7.7 角色管理
1.2.5.7.8 帐号管理
1.2.5.8 维保管理
1.2.5.8.1 维保管理
1.2.5.8.2 维保项目管理
1.2.5.8.3 登记维保记录
1.2.5.8.4 审核维保记录
1.2.5.8.5 查询维保记录
1.2.5.8.6 打印维保记录
1.2.5.9 业务管理
1.2.5.9.1 业务管理
1.2.5.9.2 查验任务状态监控
1.2.5.10 知识库管理
1.2.5.10.1 知识库管理
1.2.5.10.2 删除知识库案例
1.2.5.10.3 检索知识库案例
1.2.5.10.4 添加知识库案例
1.3 非功能需求
1.3.1 非功能需求
1.3.2 安全性
1.3.2.1 安全性
1.3.2.2 REQ905-注册的设备方可联入系统
1.3.2.3 REQ901-所有信息加密存储
1.3.2.4 REQ902-数据/消息加密传输
1.3.2.5 REQ903-授权的用户方可操作系统
1.3.2.6 REQ904-核心服务/数据多机热备
其他安全性设计
1.3.3 容错性
1.3.3.1 容错性
1.3.3.2 网络异常
1.3.3.3 节点异常
1.3.4 性能
1.3.4.1 性能
1.3.4.2 REQ921-常用操作无明显延迟感
1.3.4.3 REQ922-集中审图允许接入毫米波设备要大于等于200台
1.3.4.4 REQ923-扫描完成调度加传输时间小于等于1秒
1.3.4.5 REQ924-高稳定性
1.3.5 扩展性
1.3.5.1 扩展性
1.3.5.2 REQ941-接口化设计
1.3.5.3 REQ942-插件化设计
1.3.5.4 REQ943-模块化设计
1.3.5.5 REQ944-RESTful
1.3.5.6 REQ945-支持离线工作模式
1.3.5.7 REQ946-工作模式灵活部署
1.3.5.8 REQ947-设备节点灵活部署
1.3.5.9 REQ948-支持第三方系统集成
1.3.5.10 REQ949-支持多种分辨率
浏览器适配
其他开发任务
1.4 测试
1.4.1 安全测试
1.4.2 性能测试
1.4.3 功能测试
1.5 联调
1.6 部署和验收
1.7 编写文档
5)子模块概要设计说明书
6)UI设计效果
7)子模块测试用例说明书
8)子模块详细设计说明书(可选)
9)代码
10)系统测试报告
11)安装手册
12)操作手册

## English
Task name | Starting time | Completion time | Resource arrangement | note
1.0Pre-research and preparation
developing plan
framework
Initialize the development and test environment.
Pre-research on Message Queue Building and Interface Foundation Class
Pre-research on Scheduling Strategy Algorithms
Pre-research on Internationalization Function
requiement study
overall design
Research and Development of Parameter Configuration Function
Research and Development of Query Function
Research and Development of Command Forwarding Function
Node exception handling
Network exception handling
Research and development of interface with other modules
Research and Development of File Upload and Image Storage
Research and Development of Printing, Importing and Exporting Functions
Research and Development of Statistical Report Function
Research and Development of Scheduling Task Management Function
Research and Development of Safety Protection Function
Zabbix Construction and Basic Function Processing
1.1 UI design
1.2 Functional Requirements
1.2.1 Functional Requirements
1.2.3 Backstage Service
1.2.3.1 Backstage Service
1.2.3.2 Image Storage
1.2.3.3 Multi-to-Many, Intelligent Distribution
1.2.3.4 Storage Space Monitoring
1.2.3.5 Timing Tasks
1.2.3.6 Device Control Command Forwarding
1.2.5 Centralized Management
1.2.5.1 Centralized Management
1.2.5.2 Image Management
1.2.5.2.1 Image Management
1.2.5.2.2 Delete Image
1.2.5.2.3 Image Processing
1.2.5.2.4 Image Label Management
1.2.5.2.5 Retrieval Image
1.2.5.2.6 Preview image
1.2.5.2.7 Export Image
1.2.5.2.8 Printed Image
1.2.5.3 Data Statistics
1.2.5.3.1 Data Statistics
1.2.5.3.2 Map Checking Statistics of Judgers
1.2.5.3.3 Image Statistics
1.2.5.3.4 Hand Checker Work Statistics
1.2.5.3.5 Print statistical reports
1.2.5.3.6 Statistics of alarm items
1.2.5.3.7 alarm location statistics
1.2.5.3.8 Logon Length Statistics
1.2.5.3.9 Statistical Report Exported to Excel
1.2.5.3.10 Equipment Work Statistics
1.2.5.4 Log Management
1.2.5.4.1 Log Management
1.2.5.4.2 Query User Log
1.2.5.4.3 Query Device Boot Log
1.2.5.4.4 Query Equipment Operation Log
1.2.5.4.5 Query System Log
1.2.5.4.6 Query Operational Log
1.2.5.4.7 Export Log
1.2.5.4.8 Printed Log
1.2.5.5 Equipment Management
1.2.5.5.1 Equipment Management
1.2.5.5.2 Equipment Group Management
1.2.5.5.2.1 Equipment Group Management
1.2.5.5.2.2 Delete Device Group
1.2.5.5.2.3 Add Device Group
1.2.5.5.2.4 Rename Device Group
1.2.5.5.3 lumped parameter configuration
1.2.5.5.3.1 lumped parameter configuration
1.2.5.5.3.2 Backstage Service
1.2.5.5.3.2.1 Backstage Service
1.2.5.5.3.2.2 Image storage configuration
1.2.5.5.3.2.3 Storage Space Threshold
1.2.5.5.3.2.4 Scheduling Policy Configuration
1.2.5.5.3.2.5 Skip Blacklist Mapping Task
1.2.5.5.3.3 Examination End
1.2.5.5.3.3.1 Examination End
1.2.5.5.3.3.2 Map Examination Time for Single Map
1.2.5.5.3.3.3 Cumulative Working Time Reminder Threshold
1.2.5.5.3.4 Hand-check Station
1.2.5.5.3.4.1 Hand Check Station
1.2.5.5.3.4.2 Cumulative Work Time Reminder Threshold
1.2.5.5.3.5 device end
1.2.5.5.3.5.1 Equipment End
1.2.5.5.3.5.2 working mode
1.2.5.5.3.5.3 prompt sound switch
1.2.5.5.3.5.4 Data Preservation
1.2.5.5.3.5.5 Hand-check of this machine
1.2.5.5.3.5.6 Fuzzy Processing
1.2.5.5.3.5.7 Flow Parameter Settings
1.2.5.5.3.5.8 Shield Correction Time
1.2.5.5.3.5.9 Automatic Identification Configuration
1.2.5.5.3.5.10 equipment standby time
1.2.5.5.4 mm-wave equipment management
1.2.5.5.5 Adding Millimeter Wave Equipment
1.2.5.5.6 Editing Millimeter Wave Equipment
1.2.5.5.7 Delete Millimeter Wave Devices
1.2.5.5.8 Mapping Client Management
1.2.5.5.9 Add Mapping Client
1.2.5.5.10 Editing and Mapping Client
1.2.5.5.11 Delete Mapping Client
1.2.5.5.12 Mobile Checker Management
1.2.5.5.13 Add mobile checker
1.2.5.5.14 Editor Mobile Checker
1.2.5.5.15 Delete mobile checker
1.2.5.5.16 Centralized Monitoring
1.2.5.5.17 Card Display All Millimeter Wave Equipment
1.2.5.5.18 Card Display All Examination Clients
1.2.5.5.19 card display for all mobile checkers
1.2.5.6 Blacklist Management
1.2.5.6.1 Blacklist Management
1.2.5.6.2 Query Blacklist Personnel
1.2.5.6.3 Adding Blacklist Personnel
1.2.5.6.4 Blacklist Editors
1.2.5.7 User Management
1.2.5.7.1 User Management
1.2.5.7.2 to Outgoing User to Excel
1.2.5.7.3 Print User
1.2.5.7.4 User Rapid Location
1.2.5.7.5 User Group Management
1.2.5.7.6 Role Privilege Management
1.2.5.7.7 Role Management
1.2.5.7.8 Account Management
1.2.5.8 Maintenance Management
1.2.5.8.1 Maintenance Management
1.2.5.8.2 Maintenance Project Management
1.2.5.8.3 Registration and Maintenance Records
1.2.5.8.4 Audit and Maintenance Records
1.2.5.8.5 Query Maintenance Records
1.2.5.8.6 Print Maintenance Records
1.2.5.9 Business Management
1.2.5.9.1 Business Management
1.2.5.9.2 Check Task Status Monitoring
1.2.5.10 Knowledge Base Management
1.2.5.10.1 Knowledge Base Management
1.2.5.10.2 Deletion of Knowledge Base Cases
1.2.5.10.3 Retrieval Knowledge Base Cases
1.2.5.10.4 Adding Knowledge Base Cases
1.3 Non-functional Requirements
1.3.1 Non-functional Requirements
1.3.2 Security
1.3.2.1 Security
1.3.2.2 REQ905 - Registered equipment can be connected to the system
1.3.2.3 REQ901 - Encrypted storage of all information
1.3.2.4 REQ902-Data/Message Encrypted Transport
1.3.2.5 REQ903- authorized user can operate system
1.3.2.6 REQ904 - Core Services/Data Multi-machine Hot Standby
Other security design
1.3.3 fault tolerance
1.3.3.1 Fault Tolerance
1.3.3.2 Network Abnormality
1.3.3.3 node exception
1.3.4 Performance
1.3.4.1 Performance
1.3.4.2 REQ921 - No significant sense of delay in common operations
1.3.4.3 REQ922 - Centralized Mapping allows access to more than 200 millimeter wave devices
1.3.4.4 REQ923 - Scan completion scheduling plus transmission time less than or equal to 1 second
1.3.4.5 REQ924 - High stability
1.3.5 Extension
1.3.5.1 Extension
1.3.5.2 REQ941-Interface Design
1.3.5.3 REQ942-Plug-in Design
1.3.5.4 REQ943-Modular Design
1.3.5.5 REQ944-RESTful
1.3.5.6 REQ945 - Support offline working mode
1.3.5.7 REQ946 - Flexible deployment of working mode
1.3.5.8 REQ947 - Flexible deployment of device nodes
1.3.5.9 REQ948 - Support for third-party system integration
1.3.5.10 REQ949 - Supports multiple resolutions
Browser adaptation
Other tasks
1.4 test
1.4.1 Security Test
1.4.2 Performance Test
1.4.3 Functional Test
1.5 tune ups
1.6 Deployment and Acceptance
1.7 Documentation
5) Summary of Submodule Design
6) UI design effect
7) Submodule test case specification
8) Detailed design instructions for sub-modules (optional)
9) code
10) System Test Report
11) Installation Manual
12) Manual

## 일정
序号 | 任务名称 | 负责人 | 完成截止时间 | 备注
1 | 统一管理平台
| 权限管理模块 |  | 2019-10-11
| 机构管理 |  | 2019-10-11
| 人员管理 |  | 2019-10-11
| 权限管理 |  | 2019-10-11
| 授权管理 |  | 2019-10-11
2 | 设备管理模块 |  | 2019-10-11
| 设备分类 |  | 2019-10-11
| 档案模板 |  | 2019-10-11
| 档案管理 |  | 2019-10-11
| 设备列表 |  | 2019-10-11
| 状态监控 |  | 2019-10-11
3 | 系统设置
参数设置
场地管理
4 | 日志管理
综合业务平台
당장할것의 4를 영어로 쓸것